# Book of OHDSI meeting

June 11, 2019

Present: Martijn Schuemie, Clair Blacketer, Mui VanZandt, Anthony Sena, Sara Dempster, Hamed Abedtash, Greg Klebanov

Martijn gives a short update on what work has been done on the book in the past weeks, as well as the face-to-face meeting in Cleveland. Following up that meeting, the following people will lead these chapters:

Vocab: Christian + Mui Will work on that the next weeks

Characterization: Ellen

Incidence rate: Thomas

Cohorts: Kristin

Network Studies: Kristin

Where to begin: Hamed

Martijn would like first versions of all chapters to be done in 4 weeks, so by July 9. Greg does not think that he can make that for the network chapter. However, Kristin is already taking on most of that chapter, so should be ok. Clair also expresses concerns for the ETL chapter.  All others agree with the deadline.

Mui offers IQVIA  support to move content from Google Docs to MarkDown if that helps people meet the deadline.

Anthony: is working on characterization chapter with Dani, will work on outline, leave placeholders for work by Thomas and Ellen

Should the book have a companion website?

Anthony: we could create website as resources inside book repo, use tidy URL (created by Lee) to point to these?

Martijn asks where we should list contributors? All agree on an acknowledgement section somewhere at the start of the book. Cannot automatically derive this list from the Git commit log as Hadley did, because most contributors will not be committing.

Should we use CC0 license? No objections, but also no-one really knows that the consequences are.

Sara: will continue work on study steps